## Sheet1
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | 2025-02-12 | HTML tags and signatures not removed properly during preprocessing | Milestone 1 | Backend | Functional | Improved regex cleaning and removed HTML noise | 2025-04-12 | Closed | Clean dataset generated
2 | 2025-06-12 | Duplicate emails affecting class distribution | Milestone 1 | Backend | Data Quality | Removed duplicates and rebalanced dataset | 2025-08-12 | Closed | Dataset stabilized
3 | 14-12-2025 | Baseline classifier giving low accuracy | Milestone 2 | Backend | Algorithmic | Fine-tuned Logistic Regression and adjusted features | 16-12-2025 | Closed | Accuracy improved
4 | 19-12-2025 | DistilBERT model overfitting on training data | Milestone 2 | Backend | Model Training | Added dropout and reduced epochs | 21-12-2025 | Closed | Stable validation loss
5 | 30-12-2025 | Urgency keywords not detected correctly | Milestone 3 | Backend | Logic | Added rule-based keyword mapping | 2026-02-01 | Closed | Correct urgency levels
6 | 2026-04-01 | Incorrect urgency score for mixed emails | Milestone 3 | Backend | Functional | Combined ML + rule-based scoring | 2026-06-01 | Closed | Hybrid model validated
7 | 2026-12-01 | Streamlit app slow during first load | Milestone 4 | Backend | Performance | Cached model loading using st.cache_resource | 14-01-2026 | Closed | Reduced load time
8 | 16-01-2026 | Hugging Face model not loading on Render | Milestone 4 | Backend | Deployment | Fixed model loading logic and redeployed | 18-01-2026 | Closed | Model working live
9 | 20-01-2026 | UI stuck on “Application Loading” | Milestone 4 | Frontend | UI | Optimized startup process | 21-01-2026 | Closed | UI responsive
10 | 23-01-2026 | Minor UI alignment and text issues | Milestone 4 | Frontend | UI | Updated layout and labels | 24-01-2026 | Closed | Presentation ready